## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Chetan Katkar
PROJECT NAME: | Career Path Prediction & Guidance System
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-06-25

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Prediction & Guidance System
PROJECT ID | N.A
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | COMMENTS
1 | 2026-06-15 | TensorFlow download failed twice due to connection timeout on 351 MB file | Technical | No | For large packages, install separately with increased timeout and retries | Used `pip install --timeout=600 --retries=10 tensorflow` | Chetan Katkar | Solved | Third attempt succeeded
2 | 2026-06-17 | All 4 ML models scored ~8.3% accuracy (random chance level for 12 classes) | Technical | Yes (EDA showed uniformly distributed features) | Always verify feature-target correlation before investing time in model tuning | Ran comprehensive Mutual Information and Chi-squared analysis confirming 13/19 features have zero predictive power | Chetan Katkar | Solved | Dataset is likely synthetically generated
3 | 2026-06-17 | Column name 'interested career area ' had a trailing space causing KeyErrors | Data Quality | No | Always strip whitespace from column names before any processing | Applied .str.strip() to all text columns during preprocessing | Chetan Katkar | Solved
4 | 2026-06-20 | Unicode characters (emojis) caused UnicodeEncodeError on Windows terminal (cp1252 encoding) | Technical | No | Avoid Unicode characters in scripts meant to run on Windows command line | Replaced Unicode block character with ASCII '#' in feature_analysis.py | Chetan Katkar | Solved
5 | 2026-06-19 | Reducing 12 classes to 6 grouped categories doubled accuracy from 8% to 33% | Analytical | Yes | When model accuracy is low, try reducing the number of target classes to find if a signal exists at a broader level | Documented as a key finding for the project report | Chetan Katkar | Solved | Proves faint signal exists at macro level