## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Career Path Prediction & Guidance System
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-06-13
EXPECTED COMPLETION DATE | 2026-06-26
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To build a Machine Learning-based web application that predicts the ideal career path for students based on their skills, ratings, certifications, and interests using a dataset of 6,901 student records with 20 features.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Manual career counseling is time-consuming and inconsistent. An ML-powered system can analyze student data across 19 skill dimensions and recommend one of 12 tech career roles instantly, enabling scalable and data-driven career guidance.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 1. Train and evaluate at least 3 ML models (Decision Tree, Random Forest, XGBoost). 2. Build an interactive Streamlit web application. 3. Deploy the application to Streamlit Community Cloud for public access.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Trained ML model (best_model.pkl). 2. Interactive Streamlit web application. 3. EDA visualizations and model comparison charts. 4. Project Report and README documentation . 5. All deliverable documents (SRS, WBS, RAID Log, etc.).
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Data exploration, data preprocessing, feature encoding, model training (Decision Tree, Random Forest, XGBoost), model evaluation, Streamlit UI development, Streamlit Cloud deployment.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Real-time data collection from students, integration with university databases, mobile app development, AWS/Azure cloud infrastructure.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 intern (chetan katkar).
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Python 3.13.7, VS Code, Jupyter Notebook, scikit-learn, XGBoost, TensorFlow, Streamlit, GitHub
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | All tools used are free/open-source. No monetary cost.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Tushar Topale (Sponsor), Harshada Topale (PM), Intern (chetan katkar)
END CUSTOMER (Mention the client name.) | Students seeking data-driven career guidance
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Dataset may lack sufficient predictive signal between features and target. 2. Large library downloads (TensorFlow 351 MB) may fail on slow internet. 3. Model accuracy may be limited by dataset quality.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. The PS2_Dataset.csv is complete and usable without external data sources. 2. Python and all required libraries are compatible with the development machine. 3. Streamlit Community Cloud will remain free for deployment.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. 20-day project timeline 2. Single team member (1 intern). 3. Limited to the provided PS2_Dataset.csv only.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2026-06-15
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2026-06-16
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-06-17
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-06-20
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 2026-06-21
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 2026-06-22
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-06-26