## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Chetan Katkar
Document Created On: | 2026-06-25
Version: | 1

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Prediction & Guidance System
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | ML-powered Career Prediction Web Application
PROJECT SCOPE
PROJECT START DATE | 13-Jun-2026
PROJECT END DATE | 26-Jun-2026
OVERALL PROGRESS | Completed
SL NO | TASK NAME | START DATE | END DATE | DURATION IN DAYS | STATUS
| 1 Initiation (Requirement Gathering) | 13-Jun-2026 | 15-Jun-2026
| 1.1 Setup development environment | 13-Jun-2026 | 13-Jun-2026 | 1 | COMPLETED
| 1.2 Install Python libraries | 13-Jun-2026 | 15-Jun-2026 | 3 | COMPLETED
| 1.3 Create project folder structure | 13-Jun-2026 | 13-Jun-2026 | 1 | COMPLETED
| 2 Planning & Data Exploration | 15-Jun-2026 | 16-Jun-2026
| 2.1 Load and inspect dataset | 15-Jun-2026 | 15-Jun-2026 | 1 | COMPLETED
| 2.2 Categorical EDA | 15-Jun-2026 | 15-Jun-2026 | 1 | COMPLETED
| 2.3 Numerical EDA and visualizations | 16-Jun-2026 | 16-Jun-2026 | 1 | COMPLETED
| 3 Design (Data Preprocessing) | 16-Jun-2026 | 17-Jun-2026
| 3.1 Data cleaning (nulls, duplicates, whitespace) | 16-Jun-2026 | 16-Jun-2026 | 1 | COMPLETED
| 3.2 Encode binary and ordinal features | 16-Jun-2026 | 16-Jun-2026 | 1 | COMPLETED
| 3.3 Encode complex categorical features | 16-Jun-2026 | 17-Jun-2026 | 2 | COMPLETED
| 3.4 Train/test split (80/20 stratified) | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4 Development (Model Training & App) | 17-Jun-2026 | 20-Jun-2026
| 4.1 Train Decision Tree (baseline) | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.2 Train Random Forest | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.3 Train XGBoost | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.4 Model evaluation and comparison | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.5 Hyperparameter tuning (RandomizedSearchCV) | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.6 Save final model | 17-Jun-2026 | 17-Jun-2026 | 1 | COMPLETED
| 4.7 Feature-target correlation analysis | 19-Jun-2026 | 19-Jun-2026 | 1 | COMPLETED
| 4.8 Build Streamlit UI (step-by-step wizard) | 19-Jun-2026 | 20-Jun-2026 | 2 | COMPLETED
| 4.9 Connect model to UI | 20-Jun-2026 | 20-Jun-2026 | 1 | COMPLETED
| 5 Testing | 20-Jun-2026 | 21-Jun-2026
| 5.1 Testing and bug fixing | 20-Jun-2026 | 21-Jun-2026 | 2 | COMPLETED
| 6 Deployment | 22-Jun-2026 | 22-Jun-2026
| 6.1 Deploy to Streamlit Cloud | 22-Jun-2026 | 22-Jun-2026 | 1 | COMPLETED
| 7 Closure (Documentation) | 23-Jun-2026 | 26-Jun-2026
| 7.1 Write README.md | 23-Jun-2026 | 23-Jun-2026 | 1 | COMPLETED
| 7.2 Fill deliverable documents | 23-Jun-2026 | 25-Jun-2026 | 3 | COMPLETED
| 7.3 Create final presentation | 25-Jun-2026 | 26-Jun-2026 | 2 | COMPLETED
| 7.4 Final review and submission | 26-Jun-2026 | 26-Jun-2026 | 1 | COMPLETED